TQ IDENTIFICATION

| TQ No.: | [TQ-001] | Date: | [DD/MM/YYYY] |  |
| --- | --- | --- | --- | --- |
| Project: | [Project Name] | Response Required By: | [DD/MM/YYYY] |  |
| Raised By: | [Contractor / Engineer Name] | Raised To: | [Client / Design Engineer] |  |
| Discipline: | [Fire / Integration / Electrical / Mechanical] | Drawing / Doc Ref.: | [Ref. No.] |  |

TECHNICAL QUERY

[State the technical query clearly. Reference applicable documents, drawings, specifications, and standards. Example: This TQ relates to the routing of the control cable CTL-001 from the FACP to the Gas Cutoff Panel. Drawing ELEC-DWG-005 shows the cable routed through the kitchen area however the cable tray in this area is designated for power cables only per spec §6.2. Please confirm: (1) Can control cables share the power cable tray with segregation? (2) Or is a separate dedicated instrument cable tray required? This affects site installation planning.]

PROPOSED SOLUTION / OPTIONS

| Option | Description | Technical Justification | Cost / Programme Impact |
| --- | --- | --- | --- |
| A | Route control cable in separate conduit within existing tray | Control cables in conduit provide segregation per IEC 60228 §6.3 — acceptable in shared tray with conduit | Nil additional cost |
| B | Install dedicated 50mm instrument cable tray | Full physical segregation — preferred for long-term maintenance access | SAR [___] — 3 day delay |
| C | Re-route power cables — keep control cables in existing tray | Power cables moved to wall-mounted conduit | SAR [___] — 1 week delay |

CONTRACTOR RECOMMENDED SOLUTION

| Recommended Option: | [Option A / B / C] | Reason: | [Why this option is recommended] |  |
| --- | --- | --- | --- | --- |

CLIENT / ENGINEER RESPONSE

[Client / Engineer response. Example: Option A is approved. Control cables routed in conduit within the existing tray is acceptable per project specification. Contractor to proceed as per Option A. No drawing revision required.]

| Responded By: | [Name] | Date: | [DD/MM/YYYY] |  |
| --- | --- | --- | --- | --- |
| Signature: |  | TQ Status: | Open / Closed |  |

DISCLAIMER

Generic reference template by FreeDocumentsHub.com. Not certified advice. User assumes full responsibility.

FDH-PM-081  |  FreeDocumentsHub.com  |  doers.ifti@gmail.com  |  [DELETE THIS LINE BEFORE USE]