PROJECT DETAILS

| Project: | [Project Name] | Document No.: | [LL-REG-001] |  |
| --- | --- | --- | --- | --- |
| Client: | [Client] | Compiled By: | [PM / QC Manager] |  |
| Period Covered: | [Full project / Phase 1 / DLP] | Date: | [DD/MM/YYYY] |  |

LESSONS LEARNED REGISTER

| No. | Date | Category | Phase | Lesson Learned | Root Cause | Recommendation for Future Projects |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | [DD/MM] | Engineering | Design | Ensure FACP relay contact type (N/O vs N/C) is confirmed with FACP supplier before panel design — two rework iterations required on this project | Design review did not include FACP supplier interface data | Add FACP supplier interface data sheet as mandatory input to integration design basis checklist |
| 2 | [DD/MM] | Procurement | Procurement | Order ferrule crimping tool as part of standard panel fabrication tool kit — not available on first mobilisation causing NCR | Tool not on standard equipment list | Add ferrule crimper to mandatory tool list for all panel fabrication projects |
| 3 | [DD/MM] | Installation | Installation | Define cable tray segregation requirement in SOW before contract award — dispute arose mid-project requiring VO | Spec did not specify segregation clearly | Add cable segregation requirements table to standard SOW template |
| 4 | [DD/MM] | Commissioning | Commissioning | Build full end-to-end system test (fire alarm → gas cutoff → electrical cutoff) into SAT procedure from the start — not just individual loop tests | SAT procedure was too focused on individual components | Standard SAT procedure to include minimum 3 full scenario tests |
| 5 | [DD/MM] | HSE | All phases | Pre-mobilisation toolbox talk covering project-specific hazards (live FACP, gas lines) significantly reduced incidents compared to previous projects | Good practice identified — continue on all projects | Include project-specific hazard briefing as mandatory item on site induction checklist |
| 6 |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |
| 11 |  |  |  |  |  |  |
| 12 |  |  |  |  |  |  |
| 13 |  |  |  |  |  |  |
| 14 |  |  |  |  |  |  |
| 15 |  |  |  |  |  |  |
| 16 |  |  |  |  |  |  |
| 17 |  |  |  |  |  |  |
| 18 |  |  |  |  |  |  |
| 19 |  |  |  |  |  |  |
| 20 |  |  |  |  |  |  |

LESSONS APPLIED TO FUTURE PROJECTS

[How were lessons from previous projects applied to this project? Example: From previous project LL register: (1) FACP interface data was obtained from Siemens before design commenced — zero design rework required. (2) Ferrule crimper was included in tool kit from day one — zero NCRs for termination. (3) Cable segregation was specified in SOW — no disputes arose during installation.]

SIGN-OFF

| Prepared By: | [Name + Position] | Approved By: | [Name] |  |
| --- | --- | --- | --- | --- |
| Signature: |  | Date: | [DD/MM/YYYY] |  |

DISCLAIMER

Generic reference template by FreeDocumentsHub.com. Not certified advice. User assumes full responsibility.

FDH-PM-096  |  FreeDocumentsHub.com  |  doers.ifti@gmail.com  |  [DELETE THIS LINE BEFORE USE]