## 1. Deviation Request
DEVIATION REQUEST FORM
Submit BEFORE work begins — Request to depart from specification before execution
ISO 9001 S8.7 ¦ FIDIC ¦ PMI ¦ FreeDocumentsHub.com ¦ Template: FDH-TP-125
SECTION 1 — REQUEST IDENTIFICATION
✎ Fill all fields below. A Deviation is submitted BEFORE work begins. If work is already done — use the Concession Request form (Sheet 2).
Request No.: | DCR-001 |  | Type: | DEVIATION — Before Work Begins
Project Name: | [Your Project Name] |  | Project No.: | [Project / PO Number]
Submitted By: | [Your Company Name] |  | Submitted To: | [Client / Engineer Name]
Spec / Drawing Ref.: | [Spec Clause / Drawing No. & Rev.] |  | Response Required By: | [DD/MM/YYYY]
Date Submitted: | [DD/MM/YYYY] |  | Priority: | URGENT / NORMAL
SECTION 2 — DESCRIPTION OF DEVIATION
✎ Describe exactly what is being requested. State the specified item and the proposed alternative. Be specific — include model numbers, standards, dimensions.
Example: Request to use Schneider NSX100N circuit breaker in place of NSX100F as specified in Clause 14.3 of the Electrical Specification Rev B. Both are IEC 60947-2 compliant 100A MCCBs. The NSX100N has Ics of 25kA vs 36kA for NSX100F. Maximum fault current at SDB-01 is 18kA per CALC-001 — NSX100N is adequate. Saves SAR 450 per unit.
SECTION 3 — SPECIFICATION REQUIREMENT
✎ Quote the exact specification clause. State what the spec says and what you are proposing instead.
Specification Clause: | [Spec Clause No. — e.g. Clause 14.3 Electrical Specification Rev B]
Drawing Reference: | [Drawing No. & Revision — e.g. E-SDB-001 Rev A]
Specified Requirement: | [What the specification says exactly — copy the exact wording]
Proposed Alternative: | [What you are proposing to use or do instead — be specific]
SECTION 4 — TECHNICAL JUSTIFICATION
✎ This is the most important section. Prove the alternative meets the intent of the specification. Reference standards and calculations. Be specific.
Write your technical justification here. Include: • Technical comparison between specified and proposed item • Relevant standard references for both options (e.g. IEC 60947-2) • Calculation references if applicable (e.g. Fault Level Calc CALC-001 Rev A) • Statement of equivalence — why the alternative meets the same functional requirement • Any differences — be honest, do not hide them
SECTION 5 — IMPACT ASSESSMENT
✎ Assess all four impact areas honestly. If there is no impact — write 'None' and briefly explain why.
Safety Impact: | None — proposed item meets same safety standard IEC 60947-2 |  | Quality Impact: | None — identical performance at this fault level
Programme Impact: | Saves 2 days — proposed item available from local stock |  | Cost Impact: | SAR 450 saving per unit — SAR 2,700 total for 6 units
Permanent or Temporary? | Permanent |  | Quantity Affected: | 6 units — SDB-01 distribution board
SECTION 6 — SUPPORTING ATTACHMENTS
# | Document Title | Document No. | Rev. | Pages | Attached?
1 | Fault Level Calculation | CALC-001 | A | 3 | ✓ Attached
2 | Manufacturer Data Sheet — NSX100N | DS-NSX100N | — | 2 | ✓ Attached
3 | Technical Comparison Sheet | COMP-001 | A | 1 | ✓ Attached
4 | [Additional Document]
SECTION 7 — CLIENT / ENGINEER DECISION
✎ This section is completed by the Client or Engineer. Work must NOT begin until this section is signed and dated.
Decision: | ☐ APPROVED ☐ APPROVED WITH CONDITIONS ☐ REJECTED
Conditions / Comments: | [State conditions if approved with conditions — or reason for rejection — or N/A]
Reviewed By: | [Client / Engineer Name + Signature]
Date of Decision: | [DD/MM/YYYY]
SECTION 8 — CONTRACTOR SIGN-OFF
Prepared By: | [Name + Position] |  | Company: | [Contractor Company]
Reviewed By: | [QC Manager / PM] |  | Date: | [DD/MM/YYYY]
Signature: |  |  | Date: | [DD/MM/YYYY]
© FreeDocumentsHub.com ¦ contact@freedocumentshub.com ¦ Available 24 hours, 7 days a week ¦ Template FDH-TP-125

## 2. Concession Request
CONCESSION REQUEST FORM
Submit AFTER work is done — Request to accept work that does not fully comply with specification
ISO 9001 S8.7 ¦ FIDIC ¦ PMI ¦ FreeDocumentsHub.com ¦ Template: FDH-TP-125
SECTION 1 — REQUEST IDENTIFICATION
⚠ A Concession is submitted AFTER work is already completed. The work does not fully comply. You are requesting the client to accept it as-is. Submit immediately after discovering non-compliance — do not continue work.
Request No.: | CON-001 |  | Type: | CONCESSION — Work Already Completed
Project Name: | [Your Project Name] |  | Project No.: | [Project / PO Number]
Submitted By: | [Your Company Name] |  | Submitted To: | [Client / Engineer Name]
Spec / Drawing Ref.: | [Spec Clause / Drawing No. & Rev.] |  | Response Required By: | [DD/MM/YYYY]
Date Work Completed: | [DD/MM/YYYY] |  | Date Submitted: | [DD/MM/YYYY]
SECTION 2 — DESCRIPTION OF NON-COMPLIANCE
✎ Describe exactly what was installed or done, and exactly how it departs from the specification. Include when the non-compliance was discovered and by whom.
Example: 16mm² armoured cable was installed on circuit DB-01-C12 where 25mm² was specified in Electrical Spec Clause 12.4. The specification mismatch was identified during document review on 20/04/2026 by the site supervisor after cable installation was complete. Approximately 35 metres of cable is affected.
SECTION 3 — SPECIFICATION REQUIREMENT
✎ Quote the exact specification clause that has not been met. State what was specified and what was actually installed.
Specification Clause: | [Spec Clause No. — e.g. Clause 12.4 Electrical Specification Rev B]
Drawing Reference: | [Drawing No. & Revision]
Specified Requirement: | [What the specification requires — exact wording]
What Was Installed: | [What was actually installed — be specific — model, size, rating, standard]
Quantity / Extent: | [How many units / how many metres / what area is affected]
SECTION 4 — TECHNICAL JUSTIFICATION — WHY IT IS STILL FIT FOR PURPOSE
✎ Prove that the installed item is still fit for purpose despite the non-compliance. This is where concessions are won or lost. Be thorough, honest, and specific.
Write your technical justification here. Include: • Why the installed item is still technically acceptable • Calculation proving adequacy (e.g. voltage drop calculation showing 16mm² is adequate at actual load) • Standard references confirming compliance in other aspects • Any testing results confirming installed item performance • Honest statement of any remaining difference or limitation
SECTION 5 — IMPACT ASSESSMENT
✎ Assess all impact areas honestly. If safety is affected even slightly — state it fully. Hiding safety impact is a serious professional and legal risk.
Safety Impact: | None — installed cable adequate for actual load per calc VD-001 |  | Quality Impact: | None — performance meets project requirements
Programme Impact: | No rework required if approved — saves 5 days |  | Cost Impact: | No additional cost if approved — rework cost SAR 8,500 if rejected
Permanent or Temporary? | Permanent |  | Quantity Affected: | 35 metres — circuit DB-01-C12 only
Root Cause: | Procurement issued wrong cable size — process corrected |  | Preventive Action: | Cable schedule check added to pre-installation checklist
SECTION 6 — SUPPORTING ATTACHMENTS
# | Document Title | Document No. | Rev. | Pages | Attached?
1 | Voltage Drop Calculation — Circuit DB-01-C12 | VD-001 | A | 2 | ✓ Attached
2 | Cable Test Results — Insulation Resistance | TR-001 | — | 1 | ✓ Attached
3 | Manufacturer Data Sheet — Installed Cable | DS-CAB-16 | — | 2 | ✓ Attached
4 | [Additional Document]
SECTION 7 — CLIENT / ENGINEER DECISION
⚠ Work remains on hold pending this decision. The installed item cannot be covered, concealed, or built over until this section is signed.
Decision: | ☐ APPROVED ☐ APPROVED WITH CONDITIONS ☐ REJECTED — REWORK REQUIRED
Conditions / Comments: | [State conditions or rework requirements — or N/A if approved]
Reviewed By: | [Client / Engineer Name + Signature]
Date of Decision: | [DD/MM/YYYY]
SECTION 8 — CONTRACTOR SIGN-OFF
Prepared By: | [Name + Position] |  | Company: | [Contractor Company]
Reviewed By: | [QC Manager / PM] |  | Date: | [DD/MM/YYYY]
Signature: |  |  | Date: | [DD/MM/YYYY]
© FreeDocumentsHub.com ¦ contact@freedocumentshub.com ¦ Available 24 hours, 7 days a week ¦ Template FDH-TP-125

## 3. Quick Reference Guide
DEVIATION vs CONCESSION — QUICK REFERENCE GUIDE
FreeDocumentsHub.com ¦ ISO 9001 S8.7 ¦ FIDIC ¦ PMI
CRITERIA | DEVIATION REQUEST | CONCESSION REQUEST
When to use | BEFORE work begins | AFTER work is completed
Timing | Proactive — you identified the issue early | Reactive — issue discovered after execution
What it means | Permission to depart from spec before starting | Acceptance of non-compliant work already done
Professional signal | ✅ Shows competence and proactive management | ⚠ Signals issue was missed before work started
Can you proceed? | NO — wait for signed approval before starting | Work is done — cannot proceed further until approved
Client perception | Positive — professional approach | Neutral to negative — depends on root cause
ISO 9001 clause | Section 8.7 — Control of Nonconforming Outputs | Section 8.7 — Control of Nonconforming Outputs
FIDIC reference | Clause 13 — Variations and Adjustments | Clause 11 — Defects Liability
Approval required? | YES — signed approval before proceeding | YES — signed approval before covering or concealing work
If rejected? | Use specified item — no problem | Rework or replacement required at contractor cost
Technical justification | Prove alternative meets specification intent | Prove installed item is still fit for purpose
Calculation required? | Often yes — prove equivalence | Always yes — prove adequacy of installed item
Safety impact | Must be assessed and stated — even if none | Must be assessed carefully — hiding safety risk is serious
Programme impact | Usually saves time — that is often why it is raised | May cause delay if rework is required
Cost impact | Often a saving — state it clearly | Rework cost if rejected — state both scenarios
KEY RULE: Submit a Deviation BEFORE work. Submit a Concession AFTER work. Never proceed without written approval in either case.
© FreeDocumentsHub.com ¦ contact@freedocumentshub.com ¦ Available 24 hours, 7 days a week