## Cover Page
FreeDocumentsHub.com
Free Industrial Documents & Training — Available 24/7
FIRE ALARM SYSTEM COMMISSIONING REPORT
Conventional & Addressable Fire Alarm Systems
| Document Number | FDH-CR-FA-001
| Revision | Rev 00 — Initial Issue
| Document Type | Commissioning Report (Sample)
| Applicable Standard | NFPA 72 / BS 5839 / EN 54
| Prepared By | FreeDocumentsHub.com
| Date of Issue | May 2026
| Status | FOR REFERENCE / ADAPTATION
© FreeDocumentsHub.com ¦ www.freedocumentshub.com ¦ SAMPLE DOCUMENT

## Project Information
FIRE ALARM COMMISSIONING REPORT — PROJECT INFORMATION
FDH-CR-FA-001 ¦ Rev 00 ¦ FreeDocumentsHub.com
A. PROJECT DETAILS
Project Name / Title
Project Number / Reference
Site / Facility Name
Site Location / Address
Client / Owner
Main Contractor
Fire Alarm Sub-Contractor
Consultant / Engineer
Contract Value (SAR / USD)
B. SYSTEM DETAILS
System Type | Conventional / Addressable / Hybrid
Number of Zones / Loops
Total Detectors Installed
Total Manual Call Points
Total Sounders / VADs
FACP Make & Model
Panel Location
Applicable Standard | NFPA 72 / BS 5839 / EN 54
Battery Backup Capacity
C. COMMISSIONING TEAM
Role |  | Name | Company | Qualification | Signature
Lead Commissioning Engineer
Commissioning Technician
Site Engineer / Supervisor
Client Representative
Consultant Representative
HSE Officer
D. DOCUMENT CONTROL
Rev |  | Description | Prepared By | Date | Status
00 |  | Initial Issue — Sample Document | FreeDocumentsHub.com | May 2026 | FOR REFERENCE

## Device Schedule & Test
FIRE ALARM SYSTEM — DEVICE SCHEDULE & FUNCTIONAL TEST RECORD
FDH-CR-FA-001 ¦ Rev 00 ¦ FreeDocumentsHub.com
A. DETECTOR FUNCTIONAL TEST LOG
No. | Zone / Loop | Device Address / ID | Device Type | Location / Area | Test Method | Response Time (s) | Panel Alarm | Sounder | Result | Remarks
1 | Zone 01 / Loop 1 | A-001 | Smoke Detector — Photo | Server Room | Smoke Spray | 12 | ✓ | ✓ | PASS
2 | Zone 01 / Loop 1 | A-002 | Smoke Detector — Photo | Server Room | Smoke Spray | 15 | ✓ | ✓ | PASS
3 | Zone 01 / Loop 1 | A-003 | Heat Detector — ROR | Kitchen Area | Heat Gun | 18 | ✓ | ✓ | PASS
4 | Zone 02 / Loop 1 | A-010 | Smoke Detector — Photo | Office Area A | Smoke Spray | 11 | ✓ | ✓ | PASS
5 | Zone 02 / Loop 1 | A-011 | Multi-Sensor Detector | Office Area B | Smoke Spray | 14 | ✓ | ✓ | PASS
6 | Zone 02 / Loop 1 | A-012 | Manual Call Point | Exit — Main Door | Break Glass | — | ✓ | ✓ | PASS
7 | Zone 03 / Loop 2 | B-001 | Smoke Detector — Photo | Corridor 1 | Smoke Spray | 13 | ✓ | ✓ | PASS
8 | Zone 03 / Loop 2 | B-002 | Smoke Detector — Photo | Corridor 2 | Smoke Spray |  | ✗ | ✗ | FAIL | Device not responding — replace
9 | Zone 03 / Loop 2 | B-010 | Manual Call Point | Exit — Emergency | Break Glass | — | ✓ | ✓ | PASS
10 | Zone 04 / Loop 2 | B-020 | Sounder / VAD | Main Lobby | System Alarm | — | ✓ | ✓ | PASS
TOTAL DEVICES TESTED: | [7 empty] | 9 | 1 | PASS COUNT ¦ FAIL COUNT

## Pre-Commissioning Checklist
FIRE ALARM SYSTEM — PRE-COMMISSIONING CHECKLIST
FDH-CR-FA-001 ¦ Rev 00 ¦ FreeDocumentsHub.com
A. VISUAL INSPECTION
No. | Check Item | Method | Acceptance Criteria | Result | Remarks / Sign-Off
A-01 | All cables installed as per approved drawings and cable schedule | Visual
A-02 | Minimum 300mm separation maintained from power cables throughout | Visual
A-03 | Cable labelling complete at both ends and all junction boxes | Visual
A-04 | All cable penetrations through walls and floors fire-stopped | Visual
A-05 | FACP installed at approved location and secured to wall per manufacturer spec | Visual
A-06 | All detector bases mounted per drawing — minimum 500mm from walls and vents | Visual
A-07 | All detectors fitted to bases — confirmed dusty works are complete | Visual
A-08 | Manual call points installed at 1.4m AFF at all exit routes | Visual / Measure
A-09 | All sounders and VADs installed per drawing | Visual
A-10 | No physical damage to any device, cable or panel observed | Visual
B. ELECTRICAL TESTS
No. | Check Item | Method | Acceptance Criteria | Result | Remarks / Sign-Off
B-01 | Insulation resistance test — each cable to earth — minimum 1 MΩ | IR Tester | Min 1 MΩ
B-02 | Loop / zone wiring continuity — end-to-end resistance | Multimeter | < 2 Ω/zone
B-03 | Supply voltage at FACP terminals confirmed within spec | Multimeter | 220–240 VAC
B-04 | 24VDC output from FACP PSU confirmed | Multimeter | 24VDC ±10%
B-05 | Earth / ground continuity — panel to building earth confirmed | Multimeter | < 1 Ω
C. PANEL & SYSTEM CHECKS
No. | Check Item | Method | Acceptance Criteria | Result | Remarks / Sign-Off
C-01 | All zone / loop addresses programmed and confirmed at panel | Panel Software
C-02 | Panel normal state — no faults on energisation | Panel Display | No faults
C-03 | All device labels and zone descriptions entered correctly in panel | Panel Software
C-04 | Battery backup connected and fully charged | Panel / Meter
C-05 | Battery backup test — mains disconnected — alarm continuous for min 30 min | Test / Timer | ≥ 30 min alarm
C-06 | Standby time confirmed — system on battery with no alarm — minimum 24 hours | Test / Timer | ≥ 24 hr standby
C-07 | Panel fault indication — open loop simulation — fault LED and buzzer activate | Simulation | Fault annunciated
C-08 | Panel acknowledge and reset functions operate correctly | Functional Test
C-09 | Remote monitoring / BMS interface signal verified (if applicable) | Functional Test
C-10 | Cause & effect matrix programmed and verified per design | Panel Software
D. LIFE SAFETY OUTPUTS
No. | Check Item | Method | Acceptance Criteria | Result | Remarks / Sign-Off
D-01 | Sounder output on alarm — all sounders activate within 3 seconds | Functional Test | < 3 sec
D-02 | Sounder audibility level verified at 65 dB(A) minimum at all occupied areas | Sound Meter | ≥ 65 dB(A)
D-03 | Strobe / VAD activation confirmed on alarm | Functional Test
D-04 | Fire suppression system interface (if applicable) — signal confirmed | Functional Test
D-05 | Elevator recall signal on alarm (if applicable) — confirmed | Functional Test
D-06 | Air handling unit (AHU) shutdown on alarm (if applicable) — confirmed | Functional Test

## Cable Schedule
FIRE ALARM SYSTEM — CABLE SCHEDULE & IR TEST RECORD
FDH-CR-FA-001 ¦ Rev 00 ¦ FreeDocumentsHub.com
CABLE SCHEDULE — INSULATION RESISTANCE TEST LOG
Cable Ref | Zone / Loop | From | To | Cable Type & Spec | Route / Conduit Ref | Length (m) | IR Test (MΩ) | Continuity (Ω) | Result | Tested By
CA-001 | Zone 01 / L1 | FACP | JB-01 | FR-LSOH 1.5mm² 2C | CT-01 | 28 | ∞ | 1.2 | PASS
CA-002 | Zone 01 / L1 | JB-01 | D-A001 | FR-LSOH 1.5mm² 2C | CT-01 | 12 | ∞ | 0.8 | PASS
CA-003 | Zone 01 / L1 | JB-01 | D-A002 | FR-LSOH 1.5mm² 2C | CT-01 | 14 | ∞ | 0.9 | PASS
CA-004 | Zone 02 / L1 | FACP | JB-02 | FR-LSOH 1.5mm² 2C | CT-02 | 35 | ∞ | 1.5 | PASS
CA-005 | Zone 02 / L1 | JB-02 | MCP-01 | FR-LSOH 1.5mm² 2C | CT-02 | 8 | ∞ | 0.6 | PASS
CA-006 | Zone 03 / L2 | FACP | JB-03 | FR-LSOH 1.5mm² 2C | CT-03 | 42 | 480 | 1.8 | FAIL | IR below threshold — check route
CA-007 | 230VAC Supply | DB-01 | FACP | XLPE 2.5mm² 3C | CT-AC | 18 | ∞ | N/A | PASS

## Commissioning Sign-Off
FIRE ALARM SYSTEM — COMMISSIONING SIGN-OFF CERTIFICATE
FDH-CR-FA-001 ¦ Rev 00 ¦ FreeDocumentsHub.com
A. COMMISSIONING SUMMARY
Total Devices Installed
Total Devices Tested
Total Devices Passed
Total Devices Failed / Snagged
Outstanding Snags at Sign-Off
Date of Commissioning
Date of Snag Clearance
Overall System Status |  | PASS / CONDITIONAL PASS / FAIL
B. SNAG LIST
No. | Snag Description |  | Location | Status
1 |  |  |  | Open / Closed
2 |  |  |  | Open / Closed
3 |  |  |  | Open / Closed
4 |  |  |  | Open / Closed
5 |  |  |  | Open / Closed
6 |  |  |  | Open / Closed
7 |  |  |  | Open / Closed
8 |  |  |  | Open / Closed
9 |  |  |  | Open / Closed
10 |  |  |  | Open / Closed
C. AUTHORISATION & SIGNATURES
Role | Print Name |  | Signature | Date
Lead Commissioning Engineer
Confirmed all functional tests complete and all results recorded
Client Representative
Witnessed commissioning and accepts the system as described herein
Consultant Representative
Reviewed the commissioning report and confirms compliance
HSE Officer
Confirms all safety requirements were met during commissioning activities
📥 Download More Free Industrial Documents
Visit FreeDocumentsHub.com for free method statements, commissioning checklists, ITP templates, and training materials
www.freedocumentshub.com — Available 24 Hours, 7 Days a Week
© 2026 FreeDocumentsHub.com ¦ SAMPLE DOCUMENT — FOR REFERENCE AND ADAPTATION